## September 2019
| 2019 |  |  |  | 2020 | [11 empty] | 2021
Task | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February
Choose an AI package | bar: 2019 September
Read NEAT Documentation | bar: 2019 September
Integrate NEAT with game | bar: 2019 September to 2019 November
Write data collection software | bar: 2019 December to 2020 February
Begin data collection | bar: 2020 February
Allow data to collect | bar: 2020 February to 2020 May
Write machine learning program | bar: 2020 March to 2020 May
Build Website | bar: 2020 June to 2020 August
Write Essay | bar: 2020 September to 2020 November
Make Presentation | bar: 2020 December to 2021 January
Present | bar: 2021 February

## May 2020
| 2019 |  |  |  | 2020 | [11 empty] | 2021
Task | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Choose an AI package | bar: 2019 September
Read NEAT Documentation | bar: 2019 September
Integrate NEAT with game | bar: 2019 September to 2019 November
Write data collection software | bar: 2019 December to 2020 February
Begin data collection | bar: 2020 February
Allow data to collect | bar: 2020 February to 2020 September
Choose new AI Package | bar: 2020 March
Write machine learning program | bar: 2020 April to 2020 July
Re-Write Machine Learning Program | bar: 2020 June to 2020 September
Build Website | bar: 2020 October to 2020 December
Write Essay | bar: 2020 October to 2021 February
Make Presentation | bar: 2021 January to 2021 February
Present | bar: 2021 February to 2021 March
I have had to make changes to my Gantt Chart now due to learning new things about the NEAT package.
I have also faced set-backs due to having taken a short break earlier this year soon after we were put on lockdown.
I have learnt that there is no way to save a model for deployment with NEAT and so have had to choose a new package. I have moved from NEAT to TensorFlow.
I have determined that the data will take longer to collect if I want a meaningful machine learning model.
While I am waiting for the data to collect I will continue to build my machine learning model training code, however I am having to rewrite it due to functionality issues with my first attempt.
I have given myself longer to write my essay as I feel I will have more to talk about and so will need longer to draft and write it.
Hopefully by the time I have enough data the rest of my script will be ready so I can activate the training script and leave it running.

## October 2020
| 2019 |  |  |  | 2020 | [11 empty] | 2021
Task | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Choose an AI package | bar: 2019 September
Read NEAT Documentation | bar: 2019 September
Integrate NEAT with game | bar: 2019 September to 2019 November
Write data collection software | bar: 2019 December to 2020 February
Begin data collection | bar: 2020 February
Allow data to collect | bar: 2020 February to 2020 September
Choose new AI Package | bar: 2020 March
Write machine learning program | bar: 2020 April to 2020 July
Re-Write Machine Learning Program | bar: 2020 June to 2020 September
Build Website | bar: 2020 September to 2020 December
Write Essay | bar: 2020 October to 2021 February
Make Presentation | bar: 2021 January to 2021 February
Present | bar: 2021 February to 2021 March
I am on track
I have brought back the beginning of making my website as I finished making the training program earlier than expected.

## March 2020
| 2019 |  |  |  | 2020 | [11 empty] | 2021
Task | September | October | November | December | January | February | March | April | May | June | July | August | September | October | November | December | January | February | March
Choose an AI package | bar: 2019 September
Read NEAT Documentation | bar: 2019 September
Integrate NEAT with game | bar: 2019 September to 2019 November
Write data collection software | bar: 2019 December to 2020 February
Begin data collection | bar: 2020 February
Allow data to collect | bar: 2020 February to 2020 September
Choose new AI Package | bar: 2020 March
Write machine learning program | bar: 2020 April to 2020 July
Re-Write Machine Learning Program | bar: 2020 June to 2020 September
Build Website | bar: 2020 September to 2020 December
Write Essay | bar: 2020 October to 2021 February
Make Presentation | bar: 2021 January to 2021 February
Present | bar: 2021 March
Finished Project!